## Sheet1
PAGE 1, READ ACROSS | INPUTS, ASSUMPTIONS & COSTS |  |  | DEVELOPMENT TIMELINE |  | PAGE 2, READ ACROSS | [15 empty] | PAGE 3, READ ACROSS
INPUTS & ASSUMPTIONS | COMMENT | TOTAL COST '03 $$ | Payment Method | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10 | YEAR 11 | YEAR 12 | YEAR 13 | YEAR 14 | YEAR 15 | YEAR 16 | YEAR 17 | YEAR 18 | YEAR 19 | YEAR 20
Assembly & Site Prep
Burke Site Assembly
move Hornblowers | new site prep.; Hornblowers pays for move | est. at $50,000 for prep | TIF | bar: DEVELOPMENT TIMELINE YEAR 2
move Mather | new site prep.; moving costs negligible | est. at $50,000 for prep | TIF | bar: DEVELOPMENT TIMELINE YEAR 2
move submarine | new site prep.; moving costs negligible | est. at $50,000 for prep | TIF | bar: DEVELOPMENT TIMELINE YEAR 2
move Coast Guard | new site prep.; CG pays for move itself | est. at $150,000 for prep | TIF | bar: DEVELOPMENT TIMELINE YEAR 2
Bluffs Site Assembly
consolidate & move railroad tracks | 4 lengths of track, 2 miles each, estimated at $100,000/mile | 800000 | TIF | bar: DEVELOPMENT TIMELINE YEAR 2 to PAGE 2, READ ACROSS YEAR 3
Infrastructure Improvements
access roads w/ embedded utilities |  | est. at $18,750,000 | TIF | bar: PAGE 2, READ ACROSS YEAR 7 to PAGE 2, READ ACROSS YEAR 11
public marina | bulkheads in place; est. $100,000 for docks, | 100000 | TIF | bar: PAGE 2, READ ACROSS YEAR 3
renovate Coast Guard building to house marina services | 20,000 ft.2, at $12.50/ft.2 | 250000 | TIF | bar: PAGE 2, READ ACROSS YEAR 3
Phase I Environmentals | 3 studies, $150,000 each (dev. on Burke site, south of current shoreway, bluffs) | 450000 | TIF | bar: DEVELOPMENT TIMELINE YEAR 1 to DEVELOPMENT TIMELINE YEAR 2
Demolition of Existing Airport |  | 6725000 | FAA | bar: PAGE 2, READ ACROSS YEAR 7 to PAGE 2, READ ACROSS YEAR 8
Demolition of Aviation High School | estimated at 80,000 ft.2, at $4/ft.2 | 320000 | FAA | bar: PAGE 2, READ ACROSS YEAR 7
Buildout Assumptions
Total Residential Space | 3,864,000 ft.2
Total Leasable Space -Apartments | 2,314,000 ft.2 | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
market rate | 1,859,000 ft.2, at $110.50/ft.2 (1,430 units, 1,300 ft.2 each) | 205419500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
subsidized | 455,000 ft.2, at $110.50/ft.2 (350 units, 1,300 ft.2 each) | 50277500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Pilings | 90 pilings/6 story apt. building (6 buildings), for 540 pilings, at $10,000/piling | 5400000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Total Space -Rowhouses | 1,050,000 ft.2 | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
market rate | 750,000 ft.2, at $65.88/ft.2 (250 units, 3,000 ft.2 each) | 49410000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
subsidized | 300,000 ft.2, at $44.41/ft.2 (100 units, 3,000 ft.2 each) | 13323000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Total Space -Luxury Bluffs Townhouses | 250,000 ft.2, at $62.62/ft.2 (50 units 5,000 ft.2 each) | 15655000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 3 to PAGE 2, READ ACROSS YEAR 7
Total Space -Luxury Waterfront Townhouses w/ Boatslips | 250,000 ft.2, at $62.62/ft.2 (50 units 5,000 ft.2 each) | 15655000 | Developer Financing | bar: DEVELOPMENT TIMELINE YEAR 2 to PAGE 2, READ ACROSS YEAR 6
Total Space -Residential Surface Parking | 1,600,000 ft.2, at $1.37/ft.2 (4,000 spaces) | 2192000 | Developer Financing | bar: DEVELOPMENT TIMELINE YEAR 2 to PAGE 2, READ ACROSS YEAR 6
Total Ground Floor (apt. builings) Retail Space | 106,500 ft.2
Grocery Store/Market | 32,000 ft.2, at $78.45/ft.2 | 2510400 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Dry Cleaners | 15,000 ft.2, at $120.50/ft.2 | 1807500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Gym/Spa | 30,000 ft.2, at $109.50/ft.2 | 3285000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Community Center/Daycare | 20,000 ft.2, at $93.85/ft.2 | 1877000 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Restaurant-Pub | 3,500 ft.2, at $164.20/ft.2 | 574700 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Coffee House/Newstand | 2,000 ft.2, at $153.25/ft.2 | 306500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Breakfast/Bagel Place | 2,000 ft.2, at $153.25/ft.2 | 306500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
Sandwich Place | 2,000 ft.2, at $153.25/ft.2 | 306500 | Developer Financing | bar: PAGE 2, READ ACROSS YEAR 11 to PAGE 2, READ ACROSS YEAR 17
New Lakefront Airport
Runway Relocation | remove 6,000 yd.2 runway, build 6,500 yd.2, 345,000 yd.3 fill | 5200000 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
New Control Tower |  | 1500000 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
New Terminal | 57,500 ft.2, at $120/ft.2 | 6900000 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
80'x100' FBO Commercial Hangar | $48.83/ft.2 | 390640 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
80'x100' FBO Commercial Hangar | $48.83/ft.2 | 390640 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
100'x100' Corporate Hangar | $72/ft.2 | 720000 | FAA | bar: PAGE 2, READ ACROSS YEAR 4 to PAGE 2, READ ACROSS YEAR 6
PAGE 4, READ ACROSS | INPUTS, ASSUMPTIONS & COSTS |  |  | DEVELOPMENT TIMELINE YEAR 1: DEVELOPMENT TIMELINE; PAGE 2, READ ACROSS YEAR 3: PAGE 5, READ ACROSS; PAGE 3, READ ACROSS YEAR 19: PAGE 6, READ ACROSS
INPUTS & ASSUMPTIONS | COMMENT | TOTAL COST '03 $$ | Payment Method | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10 | YEAR 11 | YEAR 12 | YEAR 13 | YEAR 14 | YEAR 15 | YEAR 16 | YEAR 17 | YEAR 18 | YEAR 19 | YEAR 20
11,000 yd.2 Tie-Down Apron | anchors 20 aircraft | 619000 | FAA | bar: PAGE 5, READ ACROSS YEAR 4 to PAGE 5, READ ACROSS YEAR 6
Utility Infrastructure Replacement | estimate of 10,000 linear ft., at $150/linear ft. | 1500000 | FAA | bar: PAGE 5, READ ACROSS YEAR 4 to PAGE 5, READ ACROSS YEAR 6
New Charter School | 40,000 ft.2, at $93.50/ft.2 | 3740000 | Impact Fees | bar: DEVELOPMENT TIMELINE YEAR 2 to PAGE 5, READ ACROSS YEAR 3
Pilings for Charter School | 6 pilings, $10,000/piling | 60000 | Impact Fees | bar: DEVELOPMENT TIMELINE YEAR 2 to PAGE 5, READ ACROSS YEAR 3
Park Development | roughly 150 acres, at $10,000/acre | 1500000 | TIF | bar: PAGE 5, READ ACROSS YEAR 7 to PAGE 5, READ ACROSS YEAR 8
Cost Assumptions
Property Tax Rate
residential | 1.95% taxable market value for City of Cleveland
commercial | 2.5% taxable market value for City of Cleveland
Demolition Costs | $4/ft.2
Building (other than marina service center) Maintenance | developer's/charter school board's concern
Reserve $$ for Marina |  | 50000 | TIF
Parkland Property Insurance | roughly 6,950,000 ft.2, at $0.10/ft.2 | $695,000/yr.
Marina Property Insurance | roughly 50,000 ft.2, at $0.10/ft.2 | $5,000/yr.
Housing Landscaping Maintenance | developer's/owner's concern
Park Maintenance | roughly 150 acres, at $900/acre | $135,000/yr.
Replacement Reserve -apartments | developer's concern
Carrying Cost for Vacant Space -apartments | developer's concern
Lease Rollovers | n/a; 99 year groundleases assumed
General Infrastructure Maintenance & Trash Removal | estimated at $112/unit ($250,000/yr. at full buildout)
Surface Parking Snow Removal | developer's concern
CASH FLOW ANALYSIS
INPUTS | COMMENT | TOTAL AMOUNT '03 $$ |  | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10 | YEAR 11 | YEAR 12 | YEAR 13 | YEAR 14 | YEAR 15 | YEAR 16 | YEAR 17 | YEAR 18 | YEAR 19 | YEAR 20 | YEAR 21 | YEAR 22 | YEAR 23 | YEAR 24 | YEAR 25 | YEAR 26 | YEAR 27 | YEAR 28 | YEAR 29 | YEAR 30
City of Cleveland Revenues (inflation considered)
TIF Bond | 20 yr. term; 6% interest; 0.0872 dsc ratio; 5 yr. repayment freeze | 22200000 |  | YEAR 1: 22200000
Develop Impact Fees | $7,500/built unit | 3750000 |  | YEAR 3: 53571; YEAR 4: 107142; YEAR 5: 107142; YEAR 6: 107142; YEAR 7: 107142; YEAR 8: 53571; YEAR 11: 375000; YEAR 12: 375000; YEAR 13: 375000; YEAR 14: 375000; YEAR 15: 375000; YEAR 16: 375000; YEAR 17: 375000
Land Lease Fees -apartment buildings & parking | Fixed at 5% construction costs; costs $7,689/unit; 254 unit buildout per year | [12 empty] | 1953006 | 3906012 | 5859018 | 7812024 | 9765030 | 11718036 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755 | 13685755
Land Lease Fees -rowhouses & parking | Fixed at 5% construction costs; costs $9,017/unit; 50 unit buildout per year | [12 empty] | 450850 | 901700 | 1352550 | 1803400 | 2254250 | 2705100 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830 | 3155830
Land Lease Fees -townhouses & parking | Fixed at 5% construction costs; $2,244/unit; 70 unit buildout per year |  |  |  |  | 157098 | 314195 | 471293 | 628390 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490 | 785490
Residential PILOTS | 1.95% of taxable market value |  |  |  | 61055 | 180943 | 296392 | 407400 | 513968 | 555041 | 532838 | 510637 | 488436 | 1368332 | 2215424 | 3029713 | 3811199 | 4559880 | 5275759 | 5958834 | 5707007 | 5455180 | 5203354 | 4951527 | 4699700 | 4447874 | 4196047 | 3943050 | 3691224 | 3439397 | 3187570 | 2935743 | 2685027
Commercial PILOTS | 2.5% of taxable market value | [12 empty] | 24991 | 49341 | 73050 | 97118 | 118546 | 140332 | 161478 | 156993 | 152507 | 148021 | 143536 | 139050 | 134565 | 130079 | 125593 | 121108 | 116622 | 112137 | 107651 | 103165
Bluffs Residential Land Sales | $31,310/unit | 1565500 |  | YEAR 3: 223643; YEAR 4: 223643; YEAR 5: 223643; YEAR 6: 223643; YEAR 7: 223643
Bluffs Parking Land Sales | $548/unit | 5480 |  | YEAR 3: 7829; YEAR 4: 7829; YEAR 5: 7829; YEAR 6: 7829; YEAR 7: 7829
TOTALS |  |  |  | 22200000 | 61055 | 623084 | 949201 | 1217307 | 1480972 | 1679145 | 1371899 | 1296127 | 1273926 | 4957669 | 8232967 | 11474821 | 14684231 | 17858196 | 20999717 | 24122387 | 23491075 | 23234762 | 22978450 | 22722138 | 22465825 | 22209514 | 21953201 | 21695718 | 21439407 | 21183094 | 20926782 | 20670469 | 20415267
City of Cleveland Expenses
TIF Bond Revenue Expenditure | 20 yr. term; 6% interest; 0.0872 dsc ratio; 5 yr. repayment freeze | 22200000 |  | YEAR 1: -22200000
TIF Bond Debt Service | 20 yr. term; 6% interest; 0.0872 dsc ratio; 5 yr. repayment freeze | [12 empty] | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840 | -1935840
Parkland Property Insurance |  | $695,000/yr. | [7 empty] | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000 | -695000
Marina Property Insurance |  | $5,000/yr. |  |  |  | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000
Park Maintenance |  | $135,000/yr. | [7 empty] | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000 | -135000
General Infrastructure Maintenance & Trash Removal |  | $112/unit |  |  | -1120 | -3360 | -5600 | -7840 | -10080 | -11200 | -11200 | -11200 | -11200 | -45248 | -79296 | -113344 | -147504 | -181552 | -215600 | -250000 | -250000 | -250000 | -250000 | -215600 | -250000 | -250000 | -250000 | -250000 | -250000 | -250000 | -250000 | -250000 | -250000
TOTALS |  |  |  | -22200000 | -1120 | -8360 | -10600 | -12840 | -15080 | -846200 | -846200 | -846200 | -846200 | -2816088 | -2850136 | -2884184 | -2918344 | -2952392 | -2986440 | -3020840 | -3020840 | -3020840 | -3020840 | -2986440 | -3020840 | -3020840 | -3020840 | -3020840 | -3020840 | -3020840 | -3020840 | -3020840 | -3020840
PAGE 7, READ ACROSS
COST -BENEFIT ANALYSIS
Benefit to City of Cleveland = 419,868,406
Cost to City of Cleveland = $85,297,744
Cost-Benefit Ratio = 4.92
City Makes $334,570,662 over loan life ($11,152,355/yr.),
the Opportunity Cost of Not Developing Burke as Such
| RESIDENTIAL PILOT SCHEDULE |  |  | YEAR 3: PAGE 8, READ ACROSS; YEAR 19: PAGE 9, READ ACROSS
|  |  |  | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10 | YEAR 11 | YEAR 12 | YEAR 13 | YEAR 14 | YEAR 15 | YEAR 16 | YEAR 17 | YEAR 18 | YEAR 19 | YEAR 20 | YEAR 21 | YEAR 22 | YEAR 23 | YEAR 24 | YEAR 25 | YEAR 26 | YEAR 27 | YEAR 28 | YEAR 29 | YEAR 30
| Depreciated Value of Apts. Developed in yr. 11 | [12 empty] | 37299571 | 35943223 | 34586875 | 33230527 | 31874179 | 30517831 | 29161483 | 27805135 | 26448787 | 25092439 | 23736091 | 22379743 | 21023395 | 19667047 | 18310699 | 16954351 | 15598003 | 14241655 | 12885307 | 11528959
| Depreciated Value of Apts. Developed in yr. 12 | [13 empty] | 37299571 | 35943223 | 34586875 | 33230527 | 31874179 | 30517831 | 29161483 | 27805135 | 26448787 | 25092439 | 23736091 | 22379743 | 21023395 | 19667047 | 18310699 | 16954351 | 15598003 | 14241655 | 12885307
| Depreciated Value of Apts. Developed in yr. 13 | [14 empty] | 37299571 | 35943223 | 34586875 | 33230527 | 31874179 | 30517831 | 29161483 | 27805135 | 26448787 | 25092439 | 23736091 | 22379743 | 21023395 | 19667047 | 18310699 | 16954351 | 15598003 | 14241655
| Depreciated Value of Apts. Developed in yr. 14 |  |  | PAGE 8, READ ACROSS YEAR 14: 37299571; PAGE 8, READ ACROSS YEAR 15: 35943223; PAGE 8, READ ACROSS YEAR 16: 34586875; PAGE 8, READ ACROSS YEAR 17: 33230527; PAGE 8, READ ACROSS YEAR 18: 31874179; PAGE 9, READ ACROSS YEAR 19: 30517831; PAGE 9, READ ACROSS YEAR 20: 29161483; PAGE 9, READ ACROSS YEAR 21: 27805135; PAGE 9, READ ACROSS YEAR 22: 26448787; PAGE 9, READ ACROSS YEAR 23: 25092439; PAGE 9, READ ACROSS YEAR 24: 23736091; PAGE 9, READ ACROSS YEAR 25: 22379743; PAGE 9, READ ACROSS YEAR 26: 21023395; PAGE 9, READ ACROSS YEAR 27: 19667047; PAGE 9, READ ACROSS YEAR 28: 18310699; PAGE 9, READ ACROSS YEAR 29: 16954351; PAGE 9, READ ACROSS YEAR 30: 15598003
| Depreciated Value of Apts. Developed in yr. 15 |  |  | PAGE 8, READ ACROSS YEAR 15: 37299571; PAGE 8, READ ACROSS YEAR 16: 35943223; PAGE 8, READ ACROSS YEAR 17: 34586875; PAGE 8, READ ACROSS YEAR 18: 33230527; PAGE 9, READ ACROSS YEAR 19: 31874179; PAGE 9, READ ACROSS YEAR 20: 30517831; PAGE 9, READ ACROSS YEAR 21: 29161483; PAGE 9, READ ACROSS YEAR 22: 27805135; PAGE 9, READ ACROSS YEAR 23: 26448787; PAGE 9, READ ACROSS YEAR 24: 25092439; PAGE 9, READ ACROSS YEAR 25: 23736091; PAGE 9, READ ACROSS YEAR 26: 22379743; PAGE 9, READ ACROSS YEAR 27: 21023395; PAGE 9, READ ACROSS YEAR 28: 19667047; PAGE 9, READ ACROSS YEAR 29: 18310699; PAGE 9, READ ACROSS YEAR 30: 16954351
| Depreciated Value of Apts. Developed in yr. 16 |  |  | PAGE 8, READ ACROSS YEAR 16: 37299571; PAGE 8, READ ACROSS YEAR 17: 35943223; PAGE 8, READ ACROSS YEAR 18: 34586875; PAGE 9, READ ACROSS YEAR 19: 33230527; PAGE 9, READ ACROSS YEAR 20: 31874179; PAGE 9, READ ACROSS YEAR 21: 30517831; PAGE 9, READ ACROSS YEAR 22: 29161483; PAGE 9, READ ACROSS YEAR 23: 27805135; PAGE 9, READ ACROSS YEAR 24: 26448787; PAGE 9, READ ACROSS YEAR 25: 25092439; PAGE 9, READ ACROSS YEAR 26: 23736091; PAGE 9, READ ACROSS YEAR 27: 22379743; PAGE 9, READ ACROSS YEAR 28: 21023395; PAGE 9, READ ACROSS YEAR 29: 19667047; PAGE 9, READ ACROSS YEAR 30: 18310699
| Depreciated Value of Apts. Developed in yr. 17 |  |  | PAGE 8, READ ACROSS YEAR 17: 37299571; PAGE 8, READ ACROSS YEAR 18: 35943223; PAGE 9, READ ACROSS YEAR 19: 34586875; PAGE 9, READ ACROSS YEAR 20: 33230527; PAGE 9, READ ACROSS YEAR 21: 31874179; PAGE 9, READ ACROSS YEAR 22: 30517831; PAGE 9, READ ACROSS YEAR 23: 29161483; PAGE 9, READ ACROSS YEAR 24: 27805135; PAGE 9, READ ACROSS YEAR 25: 26448787; PAGE 9, READ ACROSS YEAR 26: 25092439; PAGE 9, READ ACROSS YEAR 27: 23736091; PAGE 9, READ ACROSS YEAR 28: 22379743; PAGE 9, READ ACROSS YEAR 29: 21023395; PAGE 9, READ ACROSS YEAR 30: 19667047
| Depreciated Value of Rowhouses Developed in yr. 11 | [12 empty] | 8961857 | 8635971 | 8310085 | 7984199 | 7658313 | 7332427 | 7006541 | 6680655 | 6354769 | 6028883 | 5702997 | 5377111 | 5051225 | 4725339 | 4339453 | 4073567 | 3747681 | 3421795 | 3095909 | 2770023
| Depreciated Value of Rowhouses Developed in yr. 12 | [13 empty] | 8961857 | 8635971 | 8310085 | 7984199 | 7658313 | 7332427 | 7006541 | 6680655 | 6354769 | 6028883 | 5702997 | 5377111 | 5051225 | 4725339 | 4339453 | 4073567 | 3747681 | 3421795 | 3095909
| Depreciated Value of Rowhouses Developed in yr. 13 | [14 empty] | 8961857 | 8635971 | 8310085 | 7984199 | 7658313 | 7332427 | 7006541 | 6680655 | 6354769 | 6028883 | 5702997 | 5377111 | 5051225 | 4725339 | 4339453 | 4073567 | 3747681 | 3421795
| Depreciated Value of Rowhouses Developed in yr. 14 |  |  | PAGE 8, READ ACROSS YEAR 14: 8961857; PAGE 8, READ ACROSS YEAR 15: 8635971; PAGE 8, READ ACROSS YEAR 16: 8310085; PAGE 8, READ ACROSS YEAR 17: 7984199; PAGE 8, READ ACROSS YEAR 18: 7658313; PAGE 9, READ ACROSS YEAR 19: 7332427; PAGE 9, READ ACROSS YEAR 20: 7006541; PAGE 9, READ ACROSS YEAR 21: 6680655; PAGE 9, READ ACROSS YEAR 22: 6354769; PAGE 9, READ ACROSS YEAR 23: 6028883; PAGE 9, READ ACROSS YEAR 24: 5702997; PAGE 9, READ ACROSS YEAR 25: 5377111; PAGE 9, READ ACROSS YEAR 26: 5051225; PAGE 9, READ ACROSS YEAR 27: 4725339; PAGE 9, READ ACROSS YEAR 28: 4339453; PAGE 9, READ ACROSS YEAR 29: 4073567; PAGE 9, READ ACROSS YEAR 30: 3747681
| Depreciated Value of Rowhouses Developed in yr. 15 |  |  | PAGE 8, READ ACROSS YEAR 15: 8961857; PAGE 8, READ ACROSS YEAR 16: 8635971; PAGE 8, READ ACROSS YEAR 17: 8310085; PAGE 8, READ ACROSS YEAR 18: 7984199; PAGE 9, READ ACROSS YEAR 19: 7658313; PAGE 9, READ ACROSS YEAR 20: 7332427; PAGE 9, READ ACROSS YEAR 21: 7006541; PAGE 9, READ ACROSS YEAR 22: 6680655; PAGE 9, READ ACROSS YEAR 23: 6354769; PAGE 9, READ ACROSS YEAR 24: 6028883; PAGE 9, READ ACROSS YEAR 25: 5702997; PAGE 9, READ ACROSS YEAR 26: 5377111; PAGE 9, READ ACROSS YEAR 27: 5051225; PAGE 9, READ ACROSS YEAR 28: 4725339; PAGE 9, READ ACROSS YEAR 29: 4339453; PAGE 9, READ ACROSS YEAR 30: 4073567
| Depreciated Value of Rowhouses Developed in yr. 16 |  |  | PAGE 8, READ ACROSS YEAR 16: 8961857; PAGE 8, READ ACROSS YEAR 17: 8635971; PAGE 8, READ ACROSS YEAR 18: 8310085; PAGE 9, READ ACROSS YEAR 19: 7984199; PAGE 9, READ ACROSS YEAR 20: 7658313; PAGE 9, READ ACROSS YEAR 21: 7332427; PAGE 9, READ ACROSS YEAR 22: 7006541; PAGE 9, READ ACROSS YEAR 23: 6680655; PAGE 9, READ ACROSS YEAR 24: 6354769; PAGE 9, READ ACROSS YEAR 25: 6028883; PAGE 9, READ ACROSS YEAR 26: 5702997; PAGE 9, READ ACROSS YEAR 27: 5377111; PAGE 9, READ ACROSS YEAR 28: 5051225; PAGE 9, READ ACROSS YEAR 29: 4725339; PAGE 9, READ ACROSS YEAR 30: 4339453
| Depreciated Value of Rowhouses Developed in yr. 17 |  |  | PAGE 8, READ ACROSS YEAR 17: 8961857; PAGE 8, READ ACROSS YEAR 18: 8635971; PAGE 9, READ ACROSS YEAR 19: 8310085; PAGE 9, READ ACROSS YEAR 20: 7984199; PAGE 9, READ ACROSS YEAR 21: 7658313; PAGE 9, READ ACROSS YEAR 22: 7332427; PAGE 9, READ ACROSS YEAR 23: 7006541; PAGE 9, READ ACROSS YEAR 24: 6680655; PAGE 9, READ ACROSS YEAR 25: 6354769; PAGE 9, READ ACROSS YEAR 26: 6028883; PAGE 9, READ ACROSS YEAR 27: 5702997; PAGE 9, READ ACROSS YEAR 28: 5377111; PAGE 9, READ ACROSS YEAR 29: 5051225; PAGE 9, READ ACROSS YEAR 30: 4725339
| Depreciated Value of Townhouses Developed in yr. 2 |  |  |  | 3131000 | 3017145 | 2903290 | 2789435 | 2675580 | 2561725 | 2447870 | 2334015 | 2220160 | 2106305 | 1992450 | 1878595 | 1764740 | 1650885 | 1537030 | 1423175 | 1309320 | 1195465 | 1081610 | 967755 | 853900 | 740045 | 626190 | 512335 | 398480 | 284625 | 170770 | 56885 | 0
| Depreciated Value of Townhouses Developed in yr. 3 |  |  |  |  | 6262000 | 6034290 | 5806580 | 5578870 | 5351160 | 5123450 | 4895740 | 4668030 | 4440320 | 4212610 | 3984900 | 3757190 | 3529480 | 3301770 | 3074060 | 2846350 | 2618640 | 2390930 | 2163220 | 1935510 | 1707800 | 1480090 | 1252380 | 1024670 | 796960 | 569250 | 341540 | 113830
| Depreciated Value of Townhouses Developed in yr. 4 | [5 empty] | 6262000 | 6034290 | 5806580 | 5578870 | 5351160 | 5123450 | 4895740 | 4668030 | 4440320 | 4212610 | 3984900 | 3757190 | 3529480 | 3301770 | 3074060 | 2846350 | 2618640 | 2390930 | 2163220 | 1935510 | 1707800 | 1480090 | 1252380 | 1024670 | 796960 | 569250 | 341540
| Depreciated Value of Townhouses Developed in yr. 5 | [6 empty] | 6262000 | 6034290 | 5806580 | 5578870 | 5351160 | 5123450 | 4895740 | 4668030 | 4440320 | 4212610 | 3984900 | 3757190 | 3529480 | 3301770 | 3074060 | 2846350 | 2618640 | 2390930 | 2163220 | 1935510 | 1707800 | 1480090 | 1252380 | 1024670 | 796960 | 569250
| Depreciated Value of Townhouses Developed in yr. 6 | [7 empty] | 6262000 | 6034290 | 5806580 | 5578870 | 5351160 | 5123450 | 4895740 | 4668030 | 4440320 | 4212610 | 3984900 | 3757190 | 3529480 | 3301770 | 3074060 | 2846350 | 2618640 | 2390930 | 2163220 | 1935510 | 1707800 | 1480090 | 1252380 | 1024670 | 796960
| Depreciated Value of Townhouses Developed in yr. 7 | [8 empty] | 3131000 | 3017145 | 2903290 | 2789435 | 2675580 | 2561725 | 2447870 | 2334015 | 2220160 | 2106305 | 1992450 | 1878595 | 1764740 | 1650885 | 1537030 | 1423175 | 1309320 | 1195465 | 1081610 | 967755 | 853900 | 740045 | 626190 | 512335
| TOTAL VALUE OF DEPRECIATED RESIDENTIAL PROPERTY |  |  | 0 | 3131000 | 9279145 | 15199580 | 20892305 | 26357320 | 28463625 | 27325075 | 26186525 | 25047975 | 70170853 | 113611497 | 155369907 | 195446083 | 233840025 | 270551733 | 305581207 | 292667019 | 279752831 | 266838643 | 253924455 | 241010267 | 228096079 | 215181891 | 202207703 | 189293515 | 176379327 | 163465139 | 150550921 | 137693703
| TOTAL RESIDENTIAL PILOT REVENUE (1.95% EACH MARKET VALUE $) |  |  | 0 | 61055 | 180943 | 296392 | 407400 | 513968 | 555041 | 532838 | 510637 | 488436 | 1368332 | 2215424 | 3029713 | 3811199 | 4559880 | 5275759 | 5958834 | 5707007 | 5455180 | 5203354 | 4951527 | 4699700 | 4447874 | 4196047 | 3943050 | 3691224 | 3439397 | 3187570 | 2935743 | 2685027
COMMERCIAL PILOT SCHEDULE
|  |  |  | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6 | YEAR 7 | YEAR 8 | YEAR 9 | YEAR 10 | YEAR 11 | YEAR 12 | YEAR 13 | YEAR 14 | YEAR 15 | YEAR 16 | YEAR 17 | YEAR 18 | YEAR 19 | YEAR 20 | YEAR 21 | YEAR 22 | YEAR 23 | YEAR 24 | YEAR 25 | YEAR 26 | YEAR 27 | YEAR 28 | YEAR 29 | YEAR 30
| Depreciated Value of Apartment Buildings Developed in yr. 11 | [12 empty] | 999629 | 973997 | 948365 | 922733 | 897101 | 871469 | 845837 | 820205 | 794573 | 768941 | 743309 | 717677 | 692045 | 666413 | 640781 | 615149 | 589517 | 563885 | 538253 | 512621
| Depreciated Value of Apartment Buildings Developed in yr. 12 | [13 empty] | 999629 | 973997 | 948365 | 922733 | 897101 | 871469 | 845837 | 820205 | 794573 | 768941 | 743309 | 717677 | 692045 | 666413 | 640781 | 615149 | 589517 | 563885 | 538253
| Depreciated Value of Apartment Buildings Developed in yr. 13 | [14 empty] | 999629 | 973997 | 948365 | 922733 | 897101 | 871469 | 845837 | 820205 | 794573 | 768941 | 743309 | 717677 | 692045 | 666413 | 640781 | 615149 | 589517 | 563885
| Depreciated Value of Apartment Buildings Developed in yr. 14 |  |  | YEAR 14: 999629; YEAR 15: 973997; YEAR 16: 948365; YEAR 17: 922733; YEAR 18: 897101; YEAR 19: 871469; YEAR 20: 845837; YEAR 21: 820205; YEAR 22: 794573; YEAR 23: 768941; YEAR 24: 743309; YEAR 25: 717677; YEAR 26: 692045; YEAR 27: 666413; YEAR 28: 640781; YEAR 29: 615149; YEAR 30: 589517
| Depreciated Value of Apartment Buildings Developed in yr. 15 |  |  | YEAR 15: 999629; YEAR 16: 973997; YEAR 17: 948365; YEAR 18: 922733; YEAR 19: 897101; YEAR 20: 871469; YEAR 21: 845837; YEAR 22: 820205; YEAR 23: 794573; YEAR 24: 768941; YEAR 25: 743309; YEAR 26: 717677; YEAR 27: 692045; YEAR 28: 666413; YEAR 29: 640781; YEAR 30: 615149
| Depreciated Value of Apartment Buildings Developed in yr. 16 |  |  | YEAR 16: 999629; YEAR 17: 973997; YEAR 18: 948365; YEAR 19: 922733; YEAR 20: 897101; YEAR 21: 871469; YEAR 22: 845837; YEAR 23: 820205; YEAR 24: 794573; YEAR 25: 768941; YEAR 26: 743309; YEAR 27: 717677; YEAR 28: 692045; YEAR 29: 666413; YEAR 30: 640781
| Depreciated Value of Apartment Buildings Developed in yr. 17 |  |  | YEAR 17: 999629; YEAR 18: 973997; YEAR 19: 948365; YEAR 20: 922733; YEAR 21: 897101; YEAR 22: 871469; YEAR 23: 845837; YEAR 24: 820205; YEAR 25: 794573; YEAR 26: 768941; YEAR 27: 743309; YEAR 28: 717677; YEAR 29: 692045; YEAR 30: 666413
| TOTAL VALUE OF DEPRECIATED COMMERCIAL PROPERTY |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999629 | 1973626 | 2921991 | 3844724 | 4741825 | 5613294 | 6459131 | 6279707 | 6100283 | 5920859 | 5741435 | 5562011 | 5382587 | 5203163 | 5023739 | 4844315 | 4664891 | 4485467 | 4306043 | 4126619
| TOTAL COMMERCIAL PILOT REVENUE (2.5% EACH MARKET VALUE $) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24991 | 49341 | 73050 | 97118 | 118546 | 140332 | 161478 | 156993 | 152507 | 148021 | 143536 | 139050 | 134565 | 130079 | 125593 | 121108 | 116622 | 112137 | 107651 | 103165